## Slide 1: Estimation
Notes: 1

## Slide 2: Objectives
Estimating Concepts and Principles
Virtusa 3 Level Estimation Workflow
Estimate using Virtusa Level 1 Estimation Template
Outputs of Estimation Process
Identify and Quantify Risks
Estimation Tips – General
Sample Level 1 Estimation Template

## Slide 3: Estimating Concepts and Principles

## Slide 4: Fundamentals of Estimation
Estimation is an informed approximation of Cost and Time required to
execute a task or a project (a set of tasks)
  Provides an idea of what it takes to build a desired output
  Knowledge and Experience help make the estimates accurate
Without proper Estimation
  Cost and time are wild guesses
  End up spending (usually) far more cost and time than anticipated
  Either go bankrupt or abandon the project midway through
  Whatever is spent till then goes waste
Notes: 4

## Slide 5: Fundamentals of Estimation - Contd.
Estimation as applied to Software Projects
  Provides an understanding of magnitude / quantum of work
  Enables you to identify risks, assumptions and dependencies
  Forces you to define the boundary of work
    Identify what is in scope and what is out of scope
    Helps prevent scope creep and hence keeps cost and time under control
Without proper Estimation
  Requires lot more effort than initially thought of (may we call it planned?)
  Timelines become too aggressive (lack of understanding of what it takes)
  Quality takes a serious hit (lack of time to build quality in to products)
  Results in a lot of rework (due to lack of quality in the first place)
  Resource burnout and employee turnover
  Damage to the reputation of the company
  Penalty clauses hit the revenues and profits

## Slide 6: Fundamentals of Estimation - Contd.
Steps in estimating
  Prepare – Analyze the requirements
  Size the project (code and other deliverables)
  Identify activities (requirements, design, coding etc.)
  Estimate defect potential and removal methods
  Estimate staffing needs
  Define assumptions based on experience
  Estimate effort and schedule (not directly proportionate to each other)
  Estimate development costs (inflation rate, currency exchange rates, licensing fees, travel costs etc.)
  Present estimates and defend against rejection (use prior case studies, have detailed breakdowns)

## Slide 7: Estimation Practices and Methods
Types of Estimation
  Top Down Approach (macro-estimation) – Phase or project level
    Estimate the Size of the system
    Advantages
      Consistency of estimates (independent of estimators)
      Standardization and hence better understanding
      Availability of history through the use of Organizational repository
      Effort and distribution is derived from size
    Disadvantages
      Takes longer time
  Bottom Up Approach (micro estimation) – Activity or task level
    Estimate the task effort directly
    Advantages
      Granularity of data makes them suitable for contracts and budgets
      Errors, if any, are limited to the specific activity rather than global
      New activities can be added easily, later
      Is best-suited for agile methods
    Disadvantages
      Varies greatly based on the estimators’ experience and knowledge of the system
      Actual effort may vary as the estimator is usually more experienced than the executor

## Slide 8: Inputs to Effort Estimation Process
Requirements document / RFP from the customer describing the scope of the software to be developed
Any additional information available like –
  Task Order (or) Statement of Work
  Historical information based on similar projects
  Organizational Assets – Process database
  Technologies to be used which can aid in effort estimation
  Information on Existing application
  Test artifacts (QATP, QATC, Test Strategy documents)
  Test Automation Architecture (incase of Automation assignment)

## Slide 9: 3 Point Estimation – Steps Involved
Functional decomposition of work in the form of Work Breakdown Structure (WBS)
  Task Granularity usually to the level of one day or less
Classify the tasks in to High, Medium, Low based on documented guidelines
Document the estimates of Optimistic, Most Likely and Pessimistic time required for executing each task
  Template computes the variance and standard deviation for the tasks
Identify and document the assumptions made during the estimation
Identify, document and assess the impact of risks
Consider the total effort estimated at 84% confidence level from the Estimation Summary sheet for planning
Use the effort break up (Task Estimation Type Summary table in Estimation Summary sheet) for planning

## Slide 10: Introduction to 3 – Point Estimate
"Three Point Estimation" is a technique used to estimate the time required for a project based on historical information. The 3 – P’s :
Most Optimistic ( O ) Best case scenario in which nothing goes wrong and all conditions are optimal.
Most Likely ( M ) The most likely duration and there may be some problem but a lot will go right.
Most Pessimistic ( P ) The worst case scenario which everything goes wrong
Formulae : E = ( O + 4 * M + P ) / 6
SD – ( P - ) ) / 6
E is a weighted average which takes into account (the 3 P’s) and SD measures the variability or uncertainty in the estimate.

## Slide 11: Introduction to 3 – Point Estimate – Contd.
Some tips / precautions in estimating the effort using 3 Point
  Optimistic >= 0.75 * Most Likely
    If Most likely = 8Hrs, Optimistic can at best be 6 Hrs and not less than that
  Pessimistic should be 50% to 300% more than Most Likely
    If Most likely = 8Hrs, Pessimistic can be anywhere from 12 to 42 Hrs, something like 10 Hrs is not a good estimate
  Risks should be documented and analyzed for impact
    This is important because the risk buffer for the project estimate is generated as the sum of the risk buffer for each risk
  The estimate should be taken off of the summary page
    If a single number is desired than the 84% confidence level should be used
    If a range is desired, then 50% and 98% confidence level values should be used
    NEVER take total expected effort from the detailed task estimate sheet

## Slide 12: Virtusa 3 Level Estimation Workflow

## Slide 13: Overall Estimation Workflow
Used By the Clients
For Comparison of
Vendors
Use by the Clients
For Selection of
Vendors
Used by the Clients
For Setting the SLAs
Requirement Clarity Increases
95%
Confidence
75%
Confidence
50%
Confidence
Driven by the
Feasibility
and budgeting needs
of the client. Offers
50% Confidence
level
Driven by scope
defined in Business
Requirements. Offers
25% Confidence
level
Driven by the Details
of the technical
Solution. Offers
5% Confidence
level
L0 Estimate
Assumptions
L1 Estimate
L2 Estimate
Assumptions
Assumptions Reduced
Assumptions
Notes: 13

## Slide 14: L1 Estimation
Following model is implemented as improvements
  Standardized WBS – Used the 3 point estimate template. Refined the QA tasks and added the productivity factor fore Design and Execution phase
  Mechanism to do a systematic Size estimation using
    Option 1 – If your requirements document is presented in the form of use cases, Use Case Point Factor, a separate tab has been introduced to define the Size and complexity factor of the Use cases and thereby derive the Total No. of Test cases
    Option 2 - If your requirements document is presented in the form of Business Functions, Functional point estimation model to count the No. of TCs from Data Functions and Transaction Functions Complexity using Function Point Analysis
  Mechanism to convert the size to effort using standardized productivity numbers
  Test Automation Estimate – added the Virtusa template (this could be used in the WBS to get the total effort for automation)
  Performance Testing Estimate - added the Virtusa template (this could be used in the WBS to get the total effort for Performance)
Introduce a method to use multiplication factors based on
  Size and the impact of Project risks
  Weightage of Assumptions

## Slide 15: Illustration of L1 Estimate workflow
Size Estimates
Effort Estimates
Summary Estimation Template
Standardized Work Breakdown Structure
If the BRD is in Use case
Format :
Use case factor Template
If the BRD is in Business
Functions Format :
Function Points Template
If Project has Test
Automation:
Use TA Estimation Template
If Project has Performance
Testing:
Use PT Estimation Template
Use the standard productivity
Numbers:
Test case writing efficiency
Test case review efficiency
Test Automation Efficiency
Test Execution Efficiency
Use the standard Method to
Calculate the estimate
Three point estimate
Factor to correct the estimate
on team skills
Notes: 15

## Slide 16: Estimate using Virtusa Level 1 Estimation Template

## Slide 17: Overview
Tab | Purpose
Estimation Summary | Provides Summarized details of the estimation
Size & Effort | The will be the starting point of the estimation providing the size of the testing work
Detailed Task Estimates | This is an automated sheet illustrate the detail task breakdown with estimated values
Test Automation Estimate | Will be used to estimate test automation work
Performance Testing Estimate | Will be used to estimate Performance testing work
Security Testing Estimate | Will be used to estimate Security Testing work
Assumptions | Define estimation related assumptions
Detailed Risk Impact Estimates | Define estimation related Risks

## Slide 18: Jump Start
Following 3 steps can be followed in order to perform estimation using the framework
Estimation framework has already created a set of predefined task breakdown list which covers all the aspects of the relevant work type
The estimation values will be auto generated based on the risk factors provided
Provide relevant risk factors belonging to respective testing type
Determine Type of Testing to be executed
Define Size

## Slide 19: Define Testing Size
Step | Screen Navigation
Navigate to < Project Size & Effort> tab | 
Select the Size Estimation Method | 
If Method = FP , Specify the # of Function Points | 
If Method = Use Cases, Specify Following Average Steps per flow # of Alternative flows per Scenario # of UIs or # Screens per Scenario # of average flows per Scenario Total # of Scenarios | 
Based on Above input data the Total number of projected Test Case will be auto calculated | 

## Slide 20: Estimating Manual Cycles
Step | Screen Navigation
Specify Test Case Complexity %, Time Average time to write and execute a test case Based on the inputs , following will be auto calculated Total Effort to write test cases (Person Days) Total effort to Execute test cases (Person Days) for an individual Cycle | 
Define the following test execution Details | # of Execution Cycles # of OS to be Testing & Percentage # of Browsers To Be Tested and Percentage
# of Execution Cycles
Test Execution percentage on an OS
Test Execution percentage on browser
Execution Effort Auto Calculated

## Slide 21: Define Size - Contd.
Step | Screen Navigation
Based on the inputs the final Test Execution Effort will be auto selected | 
Once the Size & Effort is filled estimation for manual test execution will be auto calculated | 
Auto calculated Estimation Values

## Slide 22: Testing Types : Test Automation Estimates
Step | Screen Navigation
Navigate to < Test Automation Estimate> tab | 
Specify the RISK Factors Framework Availability Application Complexity Test Data Availability Test Case Stability Status Application Stability Domain Knowledge Experience Application Knowledge Experience POC Requirement POC Test Case Classification Test Case Break Down Scenario Break Down Tool Used Number of Execution Cycles | 
Based on the values given the Risk factors will be auto calculated | 

## Slide 23: Testing Types : Test Automation Estimates - Contd.
Step | Screen Navigation
Based on the inputs provided the Automation Estimate will be auto generated with a predefined task breakdown | 
The relevant area in the main task breakdown sheet <Detailed Task Estimates>will be auto populated | 
A tool wise testing effort compression will be auto generated in order for you aid the decision making process | 

## Slide 24: Testing Types : Performance Testing Estimates
Step | Screen Navigation
Navigate to < Performance Testing Estimate> tab | 
Specify the RISK Factors POC Required Application Type Application complexity 3rd Party Tool Interaction Test Data preparation and complexity Test Environment preparation and complexity Domain Knowledge Experience Application Knowledge Experience Protocol Experience Clarity of business scenarios Testing type required Business process classification | 
Based on the values given the Risk factors will be auto calculated | 

## Slide 25: Testing Types : Performance Testing Estimates -Contd.
Step | Screen Navigation
Based on the inputs provided the Performance Testing Estimate will be auto generated with a predefined task breakdown | 
The relevant area in the main task breakdown sheet <Detailed Task Estimates>will be auto populated | 
A tool wise testing effort compression will be auto generated in order for you aid the decision making process | 

## Slide 26: Outputs of Estimation Process
Work Breakdown Structure
High level / revised project schedule
Assumptions list
Risk and Issues list
If a pre sales activity
  Resource Plan Options
  Input to Pricing sheet
  Input to Proposal

## Slide 27: Identify and Quantify Risks
There are four risk categories that need to be understood and quantified for every project phase
  Knowledge Risk: The risk of not understanding the complexity of the various components of the system (encapsulated in the best case, expected and worst case numbers of the top down and bottom up estimates)
  Client Risk: Risks that the client situation creates (e.g. slow decision making)
  Team Risk: Risks inherent in the Virtusa team (e.g. lack of knowledge of the technology, lack of Virtusa experience)
  Environment Risk: Risks that are outside of the control of either Virtusa or the client (e.g. third party commitments)
For each risk category, Virtusa is either protected via an assumption in the contract that when broken results in a change order or the risk is quantified in person days and added to the estimate

## Slide 28: Estimation Tips - General
Allocate time
Base estimates on historical data (actual numbers)
Refer to other QA estimates
Beware of creeping / unclear requirements
Identify all kinds of Risks
Include:
  Quality
  Documentation
  Project management
  Rework
Compare actual to estimates during execution and project close
Document assumptions

## Slide 29: Sample Level 1 Estimation Template
- Contd..
Notes: 29

## Slide 30
USA UK India Sri Lanka
Corporate Headquarters
2000 West Park Drive
Westborough, MA 01581 USA
508.389.7300
www.virtusa.com
USA INDIA SRI LANKA UK
www.virtusa.com
"Virtusa" is a trademark of the company and a registered trademark in the EU and In India.
"Productization" is a service mark of the company and a registered service mark in the United States.
"vRule" is a service mark of the company.
For more information please contact SalesInquiries@virtusa.com
Notes: 30